## Slide 1: Implementation of COMETS HD Lessons Learned from MA
Michele Cristello
IV-D Director
Massachusetts Department of Revenue
Child Support Enforcement Division

## Slide 2: COMETS HD Vision
MA CSE’s new child support system would:
allow CSE to improve performance, increase and improve customer service and be more streamlined and efficient;
support proactive rather than reactive case management, empower decision making and not let cases fall through the cracks;
be more usable for staff by integrating multiple supporting technologies;
be more secure, flexible, available and accessible and be built for the future; and
modernize our technology.

## Slide 3: COMETS HD – MA’s Original Plan
A complete system replacement that included:
all core functions of the child support system (case initiation through case closure)
all supporting functions required including data warehouse, document management and generation
all customer-facing functions including voice response, call center and customer website, and
All interfaces with external partners
The system had to meet our state’s technical standards and was to be implemented incrementally.

## Slide 4: COMETS HD – Starting Plan
At the onset of our project, our approach for the new system was a custom build with existing assets (i.e. pieces for common child support functionality) brought by the vendor.
Existing assets were anticipated by the vendor to be used in 75% of the core system while 25% would be custom built.
An incremental approach but with pretty limited increments. Document management/generation, customer website and essentially a big-bang core child support implementation.

## Slide 5: COMETS HD – Costs
Total Estimated/Actual Project Costs
Start of Project (9/2012) | $151.9M
As of 12/31/18 | $187.9M
Variance | +23.7%

## Slide 6: COMETS HD – Key Milestones
First release – document generation/management implemented in March 2014 (generally on schedule)
Second release – customer website not implemented, rolled into third and final release
Final release – big bang release implemented in January 2018 (behind original schedule)
  All core child support functions
  Customer website for case participants
  Call center and voice response technology
  Data warehouse

## Slide 7: COMETS HD – Current Status
System:
Focus on defect resolution and implementing remaining required functionality and interfaces.
Working towards System Acceptance
Preparing for Federal Certification
Organization:
Adjusting to new processes, workflows and organizational structure
Re-focusing on core child support functions and improving performance

## Slide 8: COMETS HD Lessons Learned
Key Areas (there are many!):
Existing assets vs. custom development
Amount of change at any given time; amount of effort to take on
Impact on operations and on your customers
Looks good on paper…theory v. reality
Experienced and knowledgeable resources both from the state and vendor
Technology and the rate at which it changes
Ability to support these new technologies
Preparing staff and preparing them again and again…never enough communication